## Sheet1
Date | Type | Problem summary | Technical solution summary | Efforts spent | Honest efforts | Remarks
01.03.2025 | Odata | Unable to create technical service in client 110 | Helped in creating and transporting to 110 client | 1 hr | 1 hr | issued solved over meeting and expecting 1 hr billing
02.03.2025 | Odata | Unable to realize odata service in client 110 | analysed and added client URL | 1 hr | 5 min | Not expecting any bill for the efforts
02.03.2025 | Odata | Unable to test odata in client 110 for CPI team | Consultation with CPI team | 1.30 hr |  | Only co-ordinating and didn't do much
02.03.2025 | Odata | Discussionsions with next plans - Contract, Payment recording, project plan etc, next solution expectations etc. | Consultation | 1.30 hr | 30 min | 1 to 2 hrs in total seems to be fine for the efforts spent ( Not sure )
03.03.2025 | Odata | Consultation with Payment recording | Consultation | 30 min |  | Only consultation
03.03.2505 | Odata | Analysis of Payment recorrding | Analysis | 4 hrs
03.03.2025 | OData | Consultaion with new service ( PGI Delivary and Other consultation regards to change in payment process req ) | Consultation , but Spinteg couldn’t gave proper and precise requirments regarding new req | 1hr |  | Expecting 2 to 3 hrs of billing on 03.Mar
04.03.2025 | OData | Create a new odata project with custom table | Odata coding | 3 hr | 3hr
04.03.2025 | OData | New odata service ( PGI ) | Business claimed that they are ready with the requirments , so need to check |  |  | Expecting 3 - 4 hrs of billing on 04.Mar

## Sheet2
Date | Service | Type | Description | Honnest efforts | Remarks
2025-03-01 | Odata | Consultation | Helped in creating and transporting to 110 client | 1
2025-03-02 | Odata | Consultation | High level discussions and helped CPI with initial setup | 2
2025-03-03 | Odata | Consultation and analysis | Expectation is to post an accouting doc from odata using BAPI_ACC_DOC_POST | 3 | Unable to find the test case for F-29 and later on the requirment changed
2025-03-04 | Odata | Development - Payment master | Created a odata service for - Payment master | 3 | Created a new odata service
2025-03-05 | Odata | Consultation for Vehicle allotment and delivary |  | 2 | Requirment gathering and re-itteration
2025-03-05 | Odata | Development - Vehicle allotment |  | 2 | Started the devlelopments
2025-03-06 |  |  | Not much progress
2025-03-07 | Odata | Development - Vehicle allotment , Customer , Battery and IOT | Populate 4 entities ( 3 entities are productive ) in total in 1 service - Vehcle, Primary Bat, Sec Bat and IOT along with navigations | 5 | This odata service has multiple entries and navigations so took some more time to implement it
2025-03-08 | Odata | continued developments
2025-03-10 | Master data | Consulitaion - MIC , MIP and Routing | Consultation work | NA | As per the agreement of master
2025-03-11 | Master data | Developments - MIC | MIC Development | NA | As per the agreement of master
2025-03-12 | Master data | Developments -MIP | MIP Development | NA | As per the agreement of master
2025-03-13 | Master data | Developments -Routing change | Routing | NA | As per the agreement of master
2025-03-14 |  |  | Not much progress
2025-03-15 |  |  | Not much progress
2025-03-16 | Odata | Battery Inventory, Pitstop and sale order change BAPI | Created a odata service for - Battery Inventory | 3
2025-03-17 | Odata | Sale order change BAPI , PIT Stop | Pit stop - Vehicle developments and Sale order BAPI Implementation | 4 | Pit stop vehicle and sale order block developments
2025-03-18 |  |  | Not much progress - We're working on Excel parsing in webgui
2025-03-19 |  |  | Not much progress - working on MIC and MIP minor changes
2025-03-20 | Odata | Pitstop - Battery details | Pit Stop - Battery developments | 3
2025-03-21 | Odata | Pitstop - Vehichle and Battery details | Minor changes in pit stop | 1 | Don't know if we need to capture the efforts
2025-03-22 | Odata | Consultation and developmnentsVehicle delivary and Pit stop - with CPI | Minor changes and supporting CPI for testing | 2 | Don't know if we need to capture the efforts
2025-03-23 |  |  | Not much progress
2025-03-24 |  |  | Not much progress
2025-03-25 | OData | Developments - Changes in Vehcile allotment odata, BMS , OEM , ERNAM and other fields |  | 2 | Don't know if we need to capture the efforts
2025-03-26 |  |  | Not clear about the objectives
2025-03-27 | Odata | Minor changes in Pit stop | HAS IOT , BATTSLNO, Battery model and other small changes | 1 | Don't know if we need to capture the efforts
2025-03-28 | All master | Emergency corrections | Core class, FM's etc has been changed by Roopesh, so fixing all that | 3
2025-03-29 |  |  | Not much progress
2025-03-30 |  |  | Not much progress
2025-03-31 |  | Naming convention corrections and BOM Master | Naming convention changes and BOM Master develoopment | 2 - 3 hrs | Corrected in 6 masters - Check if we need to capture this efforts
2025-04-01 | Odata | Odata changes | PitStop master, Vehicle allotment changes | 2

## Sheet3
1 | Odata vehcle master ( Already develped ) | 2
2 | odata BAPI_ACC_DOC_POST analysis | 3
3 | Payment master - custom table | 3
4 | PGI vehicle allotment , Battery and IOT | 5
5 | Sale order block | 2
6 | Battery inventory | 3
7 | Pit stop, Vehicle and battery | 4