## Sheet1
Date | Type | Problem summary | Technical solution summary | Efforts spent | Honest efforts | Remarks
01.03.2025 | Odata | Unable to create technical service in client 110 | Helped in creating and transporting to 110 client | 1 hr | 1 hr | issued solved over meeting and expecting 1 hr billing
02.03.2025 | Odata | Unable to realize odata service in client 110 | analysed and added client URL | 1 hr | 5 min | Not expecting any bill for the efforts
02.03.2025 | Odata | Unable to test odata in client 110 for CPI team | Consultation with CPI team | 1.30 hr |  | Only co-ordinating and didn't do much
02.03.2025 | Odata | Discussionsions with next plans - Contract, Payment recording, project plan etc, next solution expectations etc. | Consultation | 1.30 hr | 30 min | 1 to 2 hrs in total seems to be fine for the efforts spent ( Not sure )
03.03.2025 | Odata | Consultation with Payment recording | Consultation | 30 min |  | Only consultation
03.03.2505 | Odata | Analysis of Payment recorrding | Analysis | 4 hrs
03.03.2025 | OData | Consultaion with new service ( PGI Delivary and Other consultation regards to change in payment process req ) | Consultation , but Spinteg couldn’t gave proper and precise requirments regarding new req | 1hr |  | Expecting 2 to 3 hrs of billing on 03.Mar